List of actions - revised

ECORD Outreach meeting, Granada, Feb 14-15, 2012, Granada

EMA-ESSAC: to prepare a draft of ECORD highlights to be discussed at the next outreach meeting late August - deadline is the first half of 2012

ESSAC, Patricia: To contact ECORD teachers who took part in JR expeditions and SOR to send a report and feedback after returning to the classroom

Julia/Patricia: to prepare a presentation of IODP/ECORD for educators and students

Core replicas: Action Patricia: to revise the posters of the core replicas. The posters should tell in a paragraph what the changes mean in the replicas, explain what is relevant, few words: catchy 1-2 words. So fewest time to read. Action Patricia: how to include a copy of a poster when sending the core replica

Action Patricia : to send the ACEX core replica to IODP-Canada for a long-term use.

Patricia: To contact Co-chief Scientists to select new core replicas (that tell stories) - NJSS exp (G. Mountain, J.N. Proust)? GBREC (J. Webster, Y. Yokoyama)? Mediterranean Outflow (J. Hernandez Molina, D. Stow), Louisville? NanTroSEIZE (A. Kopf, P. Henry, S. Lallemant)?

Websites:

Patricia: to collect statistics of ECORD web sites (most visited pages) and circulate information to ESSAC and ESO

Alan: to take action for updates of the ESO web site. To find a new website professional, as the previous person who used to update the website has retired.

Action Patricia, Alan: to add contacts in the ECORD photo gallery to provide visitors (e.g. journalists) with the proper photo credit and caption.

# IODP partners

Action EMA (MB): to discuss the funding strategy about education and outreach at the next ECORD Council meeting in June.

Action All: to discuss further integration/co-ordination of outreach between IODP partners in the next IODP at our next ECORD outreach meeting in September.

Action EMA (PM): to discuss with Miyuki about the new IODP website to be uploaded in March 2012.

Action ESSAC: to connect with ECORD member countries’ national offices to raise awareness for the scientist opportunities in ECORD. In this case, e.g. to further promote interests of the Co-chief Scientists and lead the message to help scientists become aware of the available options.

Action ESSAC (Julia): to involve scientists in some communication pointers in order to help them promote and present the science.

Action ESSAC/Patricia: to ask Rudy and Bremen to distribute pictures of the Bremen Summer Schools

Action EMA (Gilbert): to discuss with the Executive Council regarding the implication of an outreach person as liaison to the ECORD FIB.

Action EMA: to distribute 4/5 slides of the new IODP/ECORD structure to the group.

Action EMA (Patricia): to ask for a demonstration copy of the new book ìReconstructing Earth’s Climate History,î written by Kristin St-John, Mark Leckie et al, at the EGU meeting.

Action Outreach Group: to meet together at IODP level to further discuss advertising the book on the ESSAC website.

JR Portcall in Lisbon

Action ESSAC (JGP)/ESO (AG)/PM: to collect and attach to the website the media coverage of the portcall in Lisbon.

Action Outreach Group:  to apply the news for such successful events as the Lisbon port call, in the search for new sources for funds, e.g. from the industry sector.

EMA: to distribute newly printed documents (ECORD Business plan, updates of the folder, etc.) to ECORD

Patricia: to distribute an update of the contents of the ECORD Newsletter to the outreach group.

Action ESO/EMA: to create a new flyer of the MSPs "inspired" from the new Chikyu flyer. The flyer will be discussed further after IMAGES is ready to join ECORD.

2-page ECORD flyer for EC

Do we need a ready document?

Action (PM): to create in collaboration with DS3F an EC-focused brochure and discuss in 2012 the question if the document is needed, at the next meeting, in accordance with (action EMA @ Council # 18).

Action EMA (PM) ESO (AS): to create IODP-ECORD presentation for the general public

Action EMA (PM): to create a preliminary draft of each of the MSP expedition presentations from the existing leaflets. Patricia will send it to ESO, ESSAC and the Co-chief Scientists.

Action EMA (PM)/ESSAC (JGP): to request from all of the ESSAC delegates to translate the English version of the IODP-country specific leaflet in their language, and possibly Russian, in order to have available presentation material for their ministries.

Action EMA (PM): to revise the Distinguished Lecturer Program PPT presentations: - New Science plan PPT: to include the new Science plan Sketch and IODP structure, to eliminate list of MSP expeditions, include slides on ACEX, Tahiti, New Jersey and GBR. - DLP PPT: to reduce the number of words, e.g. students, scholarships, grants, need short precise sentences and should include the ESSAC office contact info.

# EGU 2012, 22-27 April, Vienna

###### Action EMA (PM): to provide 4 free badges: 1 for IODP MI, 1 for ICDP, and 2 for ECORD: EMA and ESO, and reduced fee badges for people who will stand in the booth.

EMA (PM): to distribute EGU Communication Plan to the ECORD, ICDP and IODP outreach group

Press Conferences

| Action EMA (GC)/ESO (AG): to find out what would be the right way to sell the societal relevance of the J-FAST Expedition. Gilbert will approach Wataru Azuma about a media conference and live video with the Chikyu at the Townhall meeting. |
| --- |
| Action ESO (AG): to contact and ask Francisco Sierro about the possibility of a press conference concerning the Mediterranean Outflow Expedition, after which Lucas Lourens must be contacted. |  |

IODP-ICDP Townhall meeting.

Action EMA (PM): to check if there would be an opportunity for live broadcasts (Q&A interview) at EGU 2012, as Kyoshi Suyehiro sounded positive about this topic. Action EMA (GC): to distribute the programme of the Townhall meeting.

Action EMA (PM): to await for a response from Geo Cinema regarding the sent ECORD EGU attendees’ videos they had requested. EGU-GeoCinema has agreed to show the ECORD video at EGU 2012.

Booth Action:

Action EMA (PM)/ESO (AS): to further discuss in Edinburgh if the booth posters have to be updated.

Document and Goodies Actions.

Action EMA (PM): to purchase more bags for the EGU.

Action ESO (AS): to order USB keys with the ESO and IODP logos.

# V. ECORD/IODP booths at other conferences

Action EMA/ESSAC/ESO: to let Patricia know when the group can discuss in detail the MontrÈal Goldschmidt Conference, possibly before EGU.

VI. Main ECORD website

Action EMA (PM): to upgrade ECORD webpage an subpages: update list of people in ECORD, simplify and condense text, apply more images, replace the ìPublic Informationî title with ìResourcesî.

Action EMA (PM): to add more substance to the webpage content via diagrams and the ECORD new structure explanations. In addition, the following webpage items need to be altered: Databases; education; public information and press and media.

# Action Outreach Group: to keep the website updates item also on the Agenda for the Next Meeting.

Action EMA (PM): to create a Partnerships star ray, and a ìLinks with other Programsî tab. The DS3F information is to be placed under the ìLinksî tab. In addition, the DS3F text is to be edited by explaining concisely its meaning.

Action EMA (PM): to add Poland under the ìSearch ECORD Peopleî tab.

Action EMA (PM): to create a users' area for each of the two new ECORD Task Forces, accessible with a login and a password from the ECORD web site.

ECORD Photo Gallery - Actions EMA (PM) / ESSAC (JGP) / ESO (AS).

- To delete the older MSP expeditions photo gallery when the new one is completed.

- To create a link for the MSP Expeditions.

- To have several ECORD Photo Gallery contacts: Alan for MSP expeditions, Julia for Summer Schools and Patricia for the other items.

- To gather the images from different sources for the ECORD photo storage on the ECORD server.

- To collect the existing photos from the expedition participants. (EMA/ESSAC)

- to agree on a unique ID for the photos: the date.

ESO Action (AS): to determine which images should be kept.

ESO website.

Action ESO (AS): - To revise the ESO website. - To update ESO website including the Baltic Sea expedition before its implementation

Action Outreach Group: to coordinate in order not to repeat the website RSS news.

ESSAC Website

- To update Poland’s link and the upcoming workshops through ECORD;

- To post the School of Rock Reports on the ESSAC Education and Resources page: e.g. given a French teacher (Jean Luc BÈrenguer) and a Portuguese teacher (Helder Pereira) names will be provided to Julia. (ESSAC/EMA)

- To check which teachers sailed on the ACEX expedition and collect similar information for other expeditions at one place.

Open expeditions for teachers to sail.

Action ESSAC (JGP): to send Alan the USIO information regarding the expeditions that are open to teachers and for EMA and ESSAC to continue the teacher expedition open call discussion.

Action ESSAC (JGP): to start an early conversation in relation to the MSPs about calls for teachers.

Action ESSAC (JGP): to update the ìSubmit the Proposalsî page listed under the ìParticipation and sailingî tab.

Action ESSAC (JGP):

- to update and place the latest news column on the top of the webpage corner.

- to update all Calls for Application in the news, grants and scholarships.

ECORD in Wikipedia.

Actions Outreach Group:

To extract material for the ECORD wiki pages from a 7-8 page summary of the Future of ECORD document prepared by EMA. (MB, GC)

Action (EMA/ESSAC/ESO): to create and circulate a suggested text of several chapters for the ECORD wiki page amongst the group. The chapter sections are due by the EGU in Vienna, (April 23-27, 2012).

# Wiki Content Action (EMA/ESSAC/ESO): Chapter Tasks division.

# Title: ECORD within IODP.

Index list of the chapters below

Introduction (Albert)

ECORD Science (ESSAC-CE)

International ECORD Expeditions (ESO-AS)

- Science concept of MSPs: Emphasize role within IODP

- Expeditions: to determine the expeditions list

ECORD Management: different entities (EMA-GC)

- Scope

- ECORD Partnerships

- ECORD’s Structure

ECORD and Society: show that program funded by taxes and goes to society. (AS)

- How we work with the general public

ECORD Future: (EMA- GC)

Internal Expedition Links

Action EMA (PM): to fix the internal expedition links’ existing errors, edit the linked words and add images representative of the ECORD science: cores, etc.

ECORD Social Networks and ECORD online.

- Twitter

EMA (PM) to advertise IODP calls on ECORD twitter account.

- Facebook.

Action ESSAC (CE & JGP): to set up an ESSAC facebook page.

- YouTube

Action ESO (AG): to acquire the existing ECORD links within other YouTube channels, e.g. the OCEANDRILLING Channel by USIO.

EDUCATION

- Action ESO (AS): to keep the group updated about BBC’s recent interest in ECORD ("Final Frontiers") and if there is any feedback from the education programme "Speak up Scotland".

Next ECORD Outreach meeting

- Where?  When?

Action Outreach Group: to hold the next ECORD Outreach Meeting in Aix-en-Provence at CEREGE: Start September 3rd 9am until Sept 4th, 2012, or that is a 1.5 days meeting.

Action EMA (MB, GC): to organize the meeting venue.

# ESSAC/ESO/EMA Education and Outreach Task Force Meeting

February 14 –15, 2012

Instituto Andaluz de Ciencias de la Tierra (IACT), Avenida de las Palmeras, 4, Armilla, Granada.  Draft Actions

I. Review of last meeting’s action items.

Paris, February 2011 and Prague, August 2011

Patricia: to update and distribute the ECORD leaflet for approval

ESSAC office, Patricia: To contact ECORD teachers who took part in JR expeditions and SOR to send a report and feedback after returning to the classroom

Julia/Patricia: to prepare a presentation of IODP/ECORD for educators and students

Patricia: to order new core replicas:

Carlota has contacted Paula Weis (USIO curator) who still do it - she works with photos and not from the cores

Next step is to select the cores (that tell stories) - NJSS exp? GBREC? Mediterranean Outflow, Louisville? NanTroSEIZE? with co-chief scientists.

EMA-ESSAC: to prepare a draft of ECORD highlights to be discussed at the next outreach meeting late August - deadline is the first half of 2012

Patricia: to collect statistics of ECORD web sites

Alan: to take action for updates of the ESO web site

Core Replicas.

Action ESO-EMA (AG, PM): to contact Michi Strasser and co-chief scientists (Siegfried Lallemant, Achim Kopf, Pierre Henry, etc.) to check if the NanTroSEIZE cores could be considered for new core replicas.

Action EMA (PM): Modify posters. The posters should tell in a Paragraph what the changes mean in the replicas, explain what is relevant, few words: catchy 1-2 words. So fewest time to read. Action EMA (PM): how to include a copy of a poster when sending the core replica?

Action EMA (PM): to send the ACEX core replica to IODP-Canada for a long-term use.

Web statistics: website traffic and the most visited ECORD website pages.

Action EMA (PM): to circulate the Web statistics information about ESSAC and the most visited pages statistics to ESO.

Action ESO (AS): to find a new website professional, as the previous person who used to update the website has retired.

Action EMA (PM): to organise contacts in the ECORD photo gallery to provide visitors (e.g. journalists) with the proper photo credit and caption.

# II. Actions related to previous IODP Meeting events

Action EMA (MB): to discuss the funding strategy about education and outreach at the next ECORD Council meeting in June.

Action All: to discuss further integration/co-ordination of outreach between IODP partners in the next IODP at our next ECORD outreach meeting in September.

IODP website

Action EMA (PM): to discuss with Miyuki about the new IODP webpage to be uploaded in March 2012.

ECORD Participation in Expeditions.

Action ESSAC: to connect with ECORD member countries’ national offices to raise awareness for the scientist opportunities in ECORD. In this case, e.g. to further promote interests of the Co-chief Scientists and lead the message to help scientists become aware of the available options. Action ESSAC (JGP): to involve scientists in some communication pointers in order to help them promote and present the science. Action ESSAC/PM: to ask Rudy and Bremen to distribute pictures of the Bremen Summer Schools

Facility Implementation Board (FIB)

Action EMA (GC): to discuss with the Executive Council regarding the implication of an outreach person as liaison to the ECORD FIB. Action EMA: to distribute 4/5 slides of the new IODP/ECORD structure to the group.

IODP at AGU 2011, San Francisco and EGU

Action EMA (PM): to ask for a demonstration copy of the new book ìReconstructing Earth’s Climate History,î written by Kristin St-John, Mark Leckie et al, at the EGU meeting.

Action Outreach Group: to meet together at IODP level to further discuss advertising the book on the ESSAC website.

JR Lisbon port call

###### Action ESSAC (JGP)/ESO (AG)/PM: to collect and attach to the website the media coverage of the portcall in Lisbon.

Action Outreach Group: to apply the news for such successful events as the Lisbon port call, in the search for new sources for funds, e.g. from the industry sector.

# III. ECORD publications/materials

# ECORD Scientists/Funding Agencies/EC.

- EMA (PM) to distribute newly printed documents (ECORD Business plan, updates of the folder, etc.)

- Action EMA(PM): to distribute an update of the contents of the ECORD Newsletter to the outreach group.

- Action ESO/EMA: to create a new flyer of the MSPs "inspired" from the new Chikyu flyer. The flyer will be discussed further after IMAGES is ready to join ECORD.

- 2-page ECORD flyer for EC

  - Do we need a ready document?

Action (PM): to create in collaboration with DS3F an EC-focused brochure and discuss in 2012 the question if the document is needed, at the next meeting, in accordance with (action EMA @ Council # 18).

- Teachers, Students.

Action EMA (PM): to create a preliminary draft of each of the MSP expedition presentations frm the existing leaflets. Patricia will send it to ESO, ESSAC and the Co-chief Scientists.

- IODP leaflets of ECORD member countries.

Action EMA (PM)/ESSAC (JGP): to request from all of the ESSAC delegates to translate the English version of the IODP-country specific flyer in their language, and possibly Russian, in order to have available presentation material for their ministries.

Action EMA (PM) ESO (AS): to create IODP-ECORD presentation for the general public

Action EMA (PM): to revise the Distinguished Lecturer Program PPT presentations: - New Science plan PPT: to include the new Science plan Sketch and IODP structure, to eliminate list of MSP expeditions, include slides on ACEX, Tahiti, New Jersey and GBR. - DLP PPT: to reduce the number of words, e.g. students, scholarships, grants, need short precise sentences and should include the ESSAC office contact info.

# IV. EGU 2012, 22-27 April, Vienna

###### Action EMA (PM): to provide 4 free badges: 1 for IODP MI, 1 for ICDP, and 2 for ECORD: EMA and ESO, and reduced fee badges for people who will stand in the booth.

EMA (PM): to distribute EGU Communication Plan to the ECORD, ICDP and IODP outreach group

Press Conferences

| Action EMA (GC)/ESO (AG): to find out what would be the right way to sell the societal relevance of the J-FAST Expedition. Gilbert will approach Wataru Azuma about a media conference and live video with the Chikyu at the Townhall meeting. |
| --- |
| Action ESO (AG): to contact and ask Francisco Sierro about the possibility of a press conference concerning the Mediterranean Outflow Expedition, after which Lucas Lourens must be contacted. |  |

IODP-ICDP Townhall meeting.

Action EMA (PM): to check if there would be an opportunity for live broadcasts (Q&A interview) at EGU 2012, as Kyoshi Suyehiro sounded positive about this topic. Action EMA (GC): to distribute the programme of the Townhall meeting.

Action EMA (PM): to await for a response from Geo Cinema regarding the sent ECORD EGU attendees’ videos they had requested. EGU-GeoCinema has agreed to show the ECORD video at EGU 2012.

Booth Action:

Action EMA (PM)/ESO (AS): to further discuss in Edinburgh if the booth posters have to be updated.

Document and Goodies Actions.

Action EMA (PM): to purchase more bags for the EGU.

Action ESO (AS): to order USB keys with the ESO and IODP logos.

# V. ECORD/IODP booths at other conferences

Action EMA/ESSAC/ESO: to let Patricia know when the group can discuss in detail the MontrÈal Goldschmidt Conference, possibly before EGU.

VI. Main ECORD website

Action EMA (PM): to upgrade ECORD webpage an subpages: update list of people in ECORD, simplify and condense text, apply more images, replace the ìPublic Informationî title with ìResourcesî.

Action EMA (PM): to add more substance to the webpage content via diagrams and the ECORD new structure explanations. In addition, the following webpage items need to be altered: Databases; education; public information and press and media.

# Action Outreach Group: to keep the website updates item also on the Agenda for the Next Meeting.

Action EMA (PM): to create a Partnerships star ray, and a ìLinks with other Programsî tab. The DS3F information is to be placed under the ìLinksî tab. In addition, the DS3F text is to be edited by explaining concisely its meaning.

Action EMA (PM): to add Poland under the ìSearch ECORD Peopleî tab.

Action EMA (PM): to create a users' area for each of the two new ECORD Task Forces, accessible with a login and a password from the ECORD web site.

ECORD Photo Gallery - Actions EMA (PM) / ESSAC (JGP) / ESO (AS).

- To delete the older MSP expeditions photo gallery when the new one is completed.

- To create a link for the MSP Expeditions.

- To have several ECORD Photo Gallery contacts: Alan for MSP expeditions, Julia for Summer Schools and Patricia for the other items.

- To gather the images from different sources for the ECORD photo storage on the ECORD server.

- To collect the existing photos from the expedition participants. (EMA/ESSAC)

- to agree on a unique ID for the photos: the date.

ESO Action (AS): to determine which images should be kept.

ESO website.

Action ESO (AS): - To revise the ESO website. - To update ESO website including the Baltic Sea expedition before its implementation

Action Outreach Group: to coordinate in order not to repeat the website RSS news.

ESSAC Website

- To update Poland’s link and the upcoming workshops through ECORD;

- To post the School of Rock Reports on the ESSAC Education and Resources page: e.g. given a French teacher (Jean Luc BÈrenguer) and a Portuguese teacher (Helder Pereira) names will be provided to Julia. (ESSAC/EMA)

- To check which teachers sailed on the ACEX expedition and collect similar information for other expeditions at one place.

Open expeditions for teachers to sail.

Action ESSAC (JGP): to send Alan the USIO information regarding the expeditions that are open to teachers and for EMA and ESSAC to continue the teacher expedition open call discussion.

Action ESSAC (JGP): to start an early conversation in relation to the MSPs about calls for teachers.

Action ESSAC (JGP): to update the ìSubmit the Proposalsî page listed under the ìParticipation and sailingî tab.

Action ESSAC (JGP):

- to update and place the latest news column on the top of the webpage corner.

- to update all Calls for Application in the news, grants and scholarships.

ECORD in Wikipedia.

Actions Outreach Group:

To extract material for the ECORD wiki pages from a 7-8 page summary of the Future of ECORD document prepared by EMA. (MB, GC)

Action (EMA/ESSAC/ESO): to create and circulate a suggested text of several chapters for the ECORD wiki page amongst the group. The chapter sections are due by the EGU in Vienna, (April 23-27, 2012).

# Wiki Content Action (EMA/ESSAC/ESO): Chapter Tasks division.

# Title: ECORD within IODP.

Index list of the chapters below

Introduction (Albert)

ECORD Science (ESSAC-CE)

International ECORD Expeditions (ESO-AS)

- Science concept of MSPs: Emphasize role within IODP

- Expeditions: to determine the expeditions list

ECORD Management: different entities (EMA-GC)

- Scope

- ECORD Partnerships

- ECORD’s Structure

ECORD and Society: show that program funded by taxes and goes to society. (AS)

- How we work with the general public

ECORD Future: (EMA- GC)

Internal Expedition Links

Action EMA (PM): to fix the internal expedition links’ existing errors, edit the linked words and add images representative of the ECORD science: cores, etc.

ECORD Social Networks and ECORD online.

- Twitter

EMA (PM) to advertise IODP calls on ECORD twitter account.

- Facebook.

Action ESSAC (CE & JGP): to set up an ESSAC facebook page.

- YouTube

Action ESO (AG): to acquire the existing ECORD links within other YouTube channels, e.g. the OCEANDRILLING Channel by USIO.

EDUCATION

- Action ESO (AS): to keep the group updated about BBC’s recent interest in ECORD ("Final Frontiers") and if there is any feedback from the education programme "Speak up Scotland".

Next ECORD Outreach meeting

- Where?  When?

Action Outreach Group: to hold the next ECORD Outreach Meeting in Aix-en-Provence at CEREGE: Start September 3rd 9am until Sept 4th, 2012, or that is a 1.5 days meeting.

Action EMA (MB, GC): to organize the meeting venue.